## ISO 25010 Assessment
Characteristic | Current State | Target | Status
Functional Suitability | Design verified | 100% acceptance criteria pass | Pending
Performance Efficiency | Design <3s p95 | All Cerf Gates 1-8 pass | Pending
Compatibility | Not yet tested | MOD IdP integration verified | Pending
Usability | Design review completed | WCAG 2.2 AA verified | Pending
Reliability | Design for MTTF 720h | 96-hour soak test <5% drift | Pending
Security | Classification boundary designed | Two-person review sign-off | Pending
Maintainability | Code structure reviewed | Audit ledger consistency verified | Pending
Portability | No portability issues identified | Single deployment target confirmed | Pending

## Exit Criteria Assessment
Acceptance Item | Status | Evidence Link | Date
AC-R-01: All Gates 1-12 green | Pending
AC-R-02: Full suite passed in last 7 days | Pending
AC-R-03: Clause-library revision pinned and documented in release notes | Pending
AC-R-04: Flake rate <2% across 30-day rolling window | Pending
AC-R-05: Allure pass rate by feature >95% | Pending
AC-R-06: Twin-sample regression passed on latest PR | Pending
AC-R-07: Open critical defects = 0 | Pending
AC-R-08: Open major defects: documented + accepted by Panel | Pending
AC-R-09: Accessibility audit signed off | Pending
AC-R-10: Classification two-person review signed off (for any classification-touching change) | Pending
AC-R-11: Drift monitor green for 14 days | Pending
AC-R-12: Independent assurance sign-off (MAA-CTS / CAA Innovation Hub) | Pending
AC-R-13: DDH acknowledgement for v1.0 live panel use | Pending

## Gates Status
Gate ID | Gate Name | Current Status | Projected Pass
Gate 1 | Unit perf | Design complete | Week 38
Gate 2 | Integration | Design complete | Week 38
Gate 3 | Load | Design complete | Week 38
Gate 4 | Stress | Design complete | Week 38
Gate 5 | Soak | Design complete | Week 38
Gate 6 | Volume | Design complete | Week 38
Gate 7 | Security-perf | Design complete | Week 38
Gate 8 | Regression | Design complete | Week 38
Gate 9 | Keystones | Design complete | Week 38
Gate 10 | Accessibility | Design complete | Week 38
Gate 11 | Classification | Design complete | Week 38
Gate 12 | Independent assurance | Design complete | Week 38

## Twin-Sample Regression
Test Case | Last Run Time | Status
Scotland Approval (happy path) | [populate on run] | Not yet run
SORA Refusal (failure mode) | [populate on run] | Not yet run