## Dashboard
Metric | Target | Actual | RAG | Trend
Execution Progress % | 100 | 24.7 | RED | →
Pass Rate % | 95 | 91 | GREEN | →
Blocked Tests % | 5 | 8.3 | AMBER | →
Critical Defects (Open) | 0 | 3 | AMBER | →
Major Defects (Open) | 0 | 12 | AMBER | →
Minor Defects (Open) | 0 | 28 | AMBER | →
Coverage % | 100 | 28 | RED | →
Gate 1 Status | PASS | PASS | GREEN | →
Gate 2 Status | PASS | AMBER | AMBER | →
Gate 3 Status | PASS | N/A | RED | →
Twin-Sample Regression | PASS | RED | RED | →
K1 (Geofence) | PASS | DESIGNING | RED | →
K2 (C2 Link) | PASS | DESIGNING | RED | →
K3-K8 Ready | N/A | NOT TESTED | RED | →
Availability % | 99.5 | 99.7 | GREEN | →

## By Test Level
Test Level | Planned | Executed | Passed | Failed | Blocked | Pass Rate %
L1 Unit | 35 | 35 | 32 | 2 | 1 | 91.4
L2 Component | 35 | 13 | 12 | 1 | 0 | 92.3
L3 Integration | 28 | 0 | 0 | 0 | 0 | —
L4 System | 88 | 0 | 0 | 0 | 0 | —
L5 SIT | 1 | 0 | 0 | 0 | 0 | —
L6 UAT | 7 | 0 | 0 | 0 | 0 | —

## By Test Type
Test Level | Planned | Executed | Passed | Failed | Blocked | Pass Rate %
Functional | 73 | 20 | 18 | 2 | 0 | 90
NFR-Performance | 18 | 8 | 7 | 1 | 0 | 87.5
NFR-Security | 12 | 5 | 5 | 0 | 0 | 100
NFR-Usability | 8 | 0 | 0 | 0 | 0 | —
NFR-Accessibility | 10 | 0 | 0 | 0 | 0 | —
Regression | 25 | 5 | 5 | 0 | 0 | 100
Smoke | 13 | 10 | 9 | 0 | 1 | 90
Twin-Sample | 37 | 0 | 0 | 0 | 0 | —
Keystone | 36 | 0 | 0 | 0 | 0 | —

## By Priority
Test Level | Planned | Executed | Passed | Failed | Blocked | Pass Rate %
Critical | 90 | 35 | 32 | 2 | 1 | 91.4
High | 100 | 13 | 12 | 1 | 0 | 92.3
Medium | 4 | 0 | 0 | 0 | 0 | —
Low | 0 | 0 | 0 | 0 | 0 | —

## By Feature
Test Level | Planned | Executed | Passed | Failed | Blocked | Pass Rate %
F01 | 7 | 7 | 6 | 1 | 0 | 85.7
F02 | 7 | 7 | 6 | 1 | 0 | 85.7
F03 | 6 | 6 | 6 | 0 | 0 | 100
F04 | 6 | 6 | 5 | 1 | 0 | 83.3
F05 | 6 | 6 | 5 | 1 | 0 | 83.3
F06 | 6 | 6 | 6 | 0 | 0 | 100
F07 | 6 | 6 | 6 | 0 | 0 | 100
F08 | 6 | 6 | 5 | 0 | 1 | 83.3
F09 | 5 | 0 | 0 | 0 | 0 | —
F10 | 5 | 0 | 0 | 0 | 0 | —
F11 | 5 | 0 | 0 | 0 | 0 | 0
F12 | 5 | 0 | 0 | 0 | 0 | 0
F13 | 5 | 0 | 0 | 0 | 0 | 0
F14 | 5 | 0 | 0 | 0 | 0 | 0
F15 | 5 | 0 | 0 | 0 | 0 | 0
F16 | 4 | 0 | 0 | 0 | 0 | 0
F17 | 4 | 0 | 0 | 0 | 0 | 0
F18 | 4 | 0 | 0 | 0 | 0 | 0
F19 | 4 | 0 | 0 | 0 | 0 | 0
F20 | 4 | 0 | 0 | 0 | 0 | 0
F21 | 3 | 0 | 0 | 0 | 0 | 0
F22 | 3 | 0 | 0 | 0 | 0 | 0
F23 | 3 | 0 | 0 | 0 | 0 | 0
F24 | 3 | 0 | 0 | 0 | 0 | 0
F25 | 3 | 0 | 0 | 0 | 0 | 0
F26 | 3 | 0 | 0 | 0 | 0 | 0
F27 | 3 | 0 | 0 | 0 | 0 | 0
F28 | 2 | 0 | 0 | 0 | 0 | 0
F29 | 2 | 0 | 0 | 0 | 0 | 0
F30 | 2 | 0 | 0 | 0 | 0 | 0

## By Sprint
Test Level | Planned | Executed | Passed | Failed | Blocked | Pass Rate %
Sprint 1 | 10 | 8 | 7 | 0 | 0 | 100
Sprint 2 | 10 | 8 | 7 | 0 | 0 | 100
Sprint 3 | 10 | 8 | 7 | 0 | 0 | 100
Sprint 4 | 10 | 8 | 7 | 0 | 0 | 100
Sprint 5 | 10 | 8 | 7 | 0 | 0 | 100
Sprint 6 | 10 | 8 | 7 | 0 | 0 | 100
Sprint 7 | 10 | 8 | 7 | 1 | 0 | 87.5
Sprint 8 | 10 | 8 | 7 | 1 | 1 | 87.5
Sprint 9 | 10 | 0 | 0 | 0 | 0 | —
Sprint 10 | 10 | 0 | 0 | 0 | 0 | —
Sprint 11 | 10 | 0 | 0 | 0 | 0 | —
Sprint 12 | 10 | 0 | 0 | 0 | 0 | —
Sprint 13 | 10 | 0 | 0 | 0 | 0 | —
Sprint 14 | 10 | 0 | 0 | 0 | 0 | —
Sprint 15 | 10 | 0 | 0 | 0 | 0 | —
Sprint 16 | 10 | 0 | 0 | 0 | 0 | —
Sprint 17 | 10 | 0 | 0 | 0 | 0 | —
Sprint 18 | 10 | 0 | 0 | 0 | 0 | —
Sprint 19 | 10 | 0 | 0 | 0 | 0 | —
Sprint 20 | 10 | 0 | 0 | 0 | 0 | —

## Defect Summary
Severity | New | Open | In Progress | Resolved | Closed | Reopened
Critical | 1 | 3 | 0 | 0 | 0 | 0
Major | 3 | 12 | 2 | 0 | 0 | 0
Minor | 5 | 28 | 5 | 3 | 0 | 2
TOTAL DEFECTS: 43
Open (blocking): 3 Critical + 12 Major = 15
Week 8 velocity: 6 TC/day (avg 10 per sprint)

## Weekly Snapshot
Week | Phase | Executed | Passed | Failed | Blocked | Pass Rate % | Crit Defects | Coverage % | RAG
7 | Phase 2 | 44 | 40 | 3 | 1 | 90.9 | 2 | 26 | GREEN
8 | Phase 2 | 48 | 44 | 3 | 1 | 91.7 | 3 | 28 | AMBER
9 | Phase 2 | 52 | 47 | 4 | 1 | 90.4 | 4 | 30 | AMBER

## Keystone Status
Keystone | Title | Status | Notes
K1 | Geofence Independence | DESIGNING | Tests running, 5 pass, 1 pending
K2 | C2 Link Resilience | DESIGNING | Tests running, 4 pass, 1 blocked
K3 | Flight Termination | PLANNED | Awaiting classified enclave access
K4 | DAA Envelope | PLANNED | Phase 3 entry condition
K5 | ML Model Manifest | PLANNED | Phase 3 entry condition
K6 | Forensic Trail | PLANNED | Phase 4 entry condition
K7 | Evidence Integrity | PLANNED | Phase 4 entry condition
K8 | Override Audit | PLANNED | Phase 4 entry condition

## Gate Status
Gate | Title | Status | Notes
Gate 1 | Unit Test Performance | PASS | 44 of 48 tests complete, 91% pass rate
Gate 2 | Integration Test Readiness | AMBER | Infrastructure done, component tests ~40%, perf budget pending
Gate 3 | System Test Scope | NOT APPLICABLE | Not yet in scope
Gate 4 | SIT Evidence Integrity | NOT APPLICABLE | Not yet in scope
Gate 5 | UAT Readiness | NOT APPLICABLE | Not yet in scope
Gate 6 | Performance SLA | NOT APPLICABLE | Not yet in scope
Gate 7 | Security Assessment | NOT APPLICABLE | Not yet in scope
Gate 8 | Regulatory Compliance | NOT APPLICABLE | Not yet in scope
Gate 9 | Keystone Confidence | NOT APPLICABLE | Not yet in scope
Gate 10 | Coverage Adequacy | NOT APPLICABLE | Not yet in scope
Gate 11 | Defect Resolution | NOT APPLICABLE | Not yet in scope
Gate 12 | Release Readiness | NOT APPLICABLE | Not yet in scope