## Defect Log
ID | Summary | Status | Severity | Priority | Reporter | Assignee | Component | Found-in-Phase | Found-in-TC-ID | Reproduction-Steps | Expected | Actual | Progress % | Due Date
DEF-001 | Artefact Detector misses RAG matrix | In Progress | Critical | P1 | QA Team | Dev Team A | Artefact Detector | Phase 1 | TC-045 | Upload ConOps | Matrix generated | Matrix missing | 75 | 2026-04-25
DEF-002 | Coverage Matrix timeout >10min | New | Critical | P1 | QA Team | Perf Team | Coverage Matrix | Phase 2 | TC-087 | Load complex submission | Response <10min | Response 15min | 0 | 2026-04-26
DEF-003 | Classification Boundary SECRET spillage | Fixed | Critical | P1 | QA Team | Security | Classification Boundary | Phase 2 | TC-112 | Upload SECRET | Redacted | Visible | 100 | 2026-04-24
DEF-004 | Audit Ledger missing override trail | Verified | Critical | P1 | QA Team | Dev Team B | Audit Ledger | Phase 3 | TC-156 | Panel override | Logged | Missing | 100 | 2026-04-24
DEF-005 | IdP SAML token expiry | In Progress | Major | P2 | Security | Auth Team | MOD/CAA IdP | Phase 1 | TC-023 | Login with SAML | Re-auth | Crash | 50 | 2026-04-27
DEF-006 | Evidence Store S3 replication lag | New | Major | P2 | Infra Team | Cloud Team | Evidence Store | Phase 2 | TC-089 | Upload file | Replicated | 5min lag | 0 | 2026-04-28
DEF-007 | Clause Library version sync delay | In Progress | Major | P2 | QA Team | Governance | Clause Library | Phase 1 | TC-065 | Release v2.1 | 5min fetch | 60min fetch | 60 | 2026-04-26
DEF-008 | WCAG contrast Panel UI | Fixed | Major | P2 | Accessibility | Dev Team A | Panel UI | Phase 2 | TC-134 | Panel case view | WCAG AA pass | Fail | 100 | 2026-04-24
DEF-009 | Keyboard nav dropdown closed early | In Progress | Major | P2 | QA Team | Dev Team C | Applicant UI | Phase 1 | TC-042 | Tab dropdown | Menu open | Menu closes | 40 | 2026-04-27
DEF-010 | Screen reader evidence list blank | New | Major | P2 | Accessibility | Dev Team B | Evidence View | Phase 2 | TC-143 | Load submission | Items announced | No items | 0 | 2026-04-28
DEF-011 | Panel log >500ms SLA | In Progress | Minor | P3 | Perf Team | Dev Team A | Panel Action Log | Phase 2 | TC-176 | 10 panel actions | <500ms each | 800ms+ | 35 | 2026-04-29
DEF-012 | Concurrency limit hit at 12 | Fixed | Minor | P3 | Load Team | Perf Team | API Gateway | Phase 2 | TC-198 | 15 concurrent | All succeed | Fail at 12 | 100 | 2026-04-24
DEF-013 | RTM clause-id-null mapping | In Progress | Minor | P3 | QA Team | Dev Team C | RTM Engine | Phase 3 | TC-167 | Generate RTM | No nulls | 3 nulls | 25 | 2026-04-30
DEF-014 | Regression baseline outdated | New | Minor | P3 | QA Team | Automation | CI/CD Pipeline | Phase 2 | TC-201 | Run regression | Current baseline | >30d old | 0 | 2026-05-01
DEF-015 | Evidence masking edge case | Fixed | Low | P4 | QA Team | Dev Team B | Data Masking | Phase 1 | TC-078 | NHS edge case | Masked | Partial | 100 | 2026-04-24