## DailyStatus
Date | Planned | Completed | Blockers | Risks
2026-04-20 | TC-FN-001 to TC-FN-005 | 3/5 TCs | None | Test data delayed 1 day
2026-04-21 | TC-FN-006 to TC-FN-010 | 5/5 TCs | Artefact parser bug (fixed) | None
2026-04-22 | TC-KS-K1-001 to TC-KS-K1-005 | 4/5 TCs | K1 mock env timeout | Regression risk if not resolved
2026-04-23 | TC-KS-K2-001 to TC-KS-K2-003 | 2/3 TCs (in progress) | None | Performance baseline drifting
2026-04-24 | TC-KS-K3/K4 integration | 0/5 (planned) | Waiting for K1 fix | Schedule slip if K1 takes >2 days