## Effort
Phase | Planned Hours | Actual Hours | Cost (GBP)
Design & Planning | 200 | 210 | 3150
Test Automation Dev | 400 | 420 | 6300
Functional Testing | 600 | 650 | 9750
Performance Testing | 300 | 280 | 4200
Security & A11y | 200 | 210 | 3150
UAT Coordination | 250 | 240 | 3600
Defect Analysis & Root Cause | 150 | 170 | 2550
Test Reporting & Sign-off | 100 | 100 | 1500
TOTAL
Cost per Defect (Major)
Cost per Defect (Minor)