## Governance
Decision/Checkpoint | Authority | Escalation Path | SLA | Documentation
Release to UAT | Test Manager | Steering Committee if blocked | 24h | Go/no-go checklist
Release to Prod | DDH + MAA LI | CAA/MAA Joint Steering if escalated | 48h | Sign-off sheet
Accept UAT defect | MAA Lead Inspector | CAA/MAA if safety-critical | 24h | Waiver form
Override audit trail | QA Lead + RAISO | Steering Committee if data-sensitive | 12h | Change control
Security gate sign-off | InfoSec Lead | RAISO if unresolved | 24h | Security report
Keystones K1-K8 confidence | MAA-CTS independent reviewer | DDH if below 9/10 | 48h | Assurance case
Twin-sample regression complete | Release Manager | Test Manager if failed | Same-day | Execution report
Drift monitor green | QA Lead | Test Manager if drift >5% | Daily check | Monitoring dashboard