## Debriefing
Finding ID | Category | Severity | Description | Impact | Recommendation | Status
F001 | Usability | Low | Form labels unclear for 'Duty Holder' field | User confusion, longer intake time | Clarify label or add tooltip | Open
F002 | Performance | High | Coverage matrix compute takes 45 sec (exceeds 10 sec SLA) | Applicants frustrated, timeout risk | Optimize algorithm, add progress bar | In Progress
F003 | Security | Critical | Password field visible in URL parameter on error | Credential exposure risk | Use POST, sanitize error messages | Blocked
F004 | Accessibility | Medium | File upload button not keyboard accessible | Screen reader users cannot upload | Add <label> element, test with NVDA | Open
F005 | Edge case | Low | Very large PDF (50 MB) uploads but scans slowly | Performance degradation, no timeout | Set max file size or async scanning | Open
F006 | Data quality | Medium | Postcode validation accepts invalid UK postcodes | Bad data in system, feedback affected | Use Royal Mail postcode API | Open
F007 | Regression | High | Revision pinning button missing in v1.3 UI | Users cannot lock revision (critical feature) | Restore button, test regression | Blocked
F008 | Concurrency | High | Two concurrent submissions from same user both mark as 'active' | Confusion, duplicate processing | Implement locking at DB level | In Progress
F009 | Usability | Low | Feedback items 15+ items hard to scan, no grouping | Cognitive load, user overwhelm | Group by category or priority | Open
F010 | Compliance | Critical | Audit log missing entries for authority override actions | Non-compliance with audit trail SOP | Hook override endpoint to audit service | Blocked