## T-Shirt Sizing
ID | Deliverable | T-Shirt Size | Ideal Hours | Rationale | Dependencies
D-001 | Test Strategy | M | 12-16 | Standard planning effort | None
D-002 | Risk Matrix | S | 6-8 | Straightforward risk assessment | Test Strategy
D-003 | RTM 100 clauses | L | 24-32 | Comprehensive mapping required | Test Strategy
D-004 | E2E Happy Path (1) | M | 12-16 | Single main flow | RTM
D-005 | E2E Refusal Path (1) | L | 20-24 | Complex failure scenarios | RTM
D-006 | E2E Boundary Path (1) | XL | 32-40 | Parameter sweeps, edge cases | RTM
D-007 | Integration Pair (1) | S | 4-6 | Single two-system interface | RTM
D-008 | Integration Suite (20) | L | 20-24 | Full integration coverage | D-007 x20
D-009 | Decision Table (1) | M | 10-14 | Medium complexity logic | RTM
D-010 | Automation Framework | XL | 40-48 | Full CI/CD + keyword library | None
D-011 | API Endpoint Test (1) | S | 4-6 | Single REST endpoint | Automation Framework
D-012 | UI E2E Script (1) | L | 16-20 | Multi-step UI automation | Automation Framework
D-013 | Data Pack Assembly (1) | M | 10-14 | Fixture + synthetic masking | None
D-014 | Test Execution Report | M | 12-16 | Results + charts + summary | All test scripts
D-015 | Defect Triage | S | 4-8 | Bug prioritisation & regression | Test Execution
D-016 | Load Test Scenario (1) | L | 16-20 | JMeter + ramp-up + analysis | Automation Framework
D-017 | Security Scan | M | 10-14 | OWASP Top 10 + OAuth testing | API documentation
D-018 | Accessibility Audit | M | 10-14 | WCAG 2.1 Level AA spot checks | UI mockups
D-019 | Exploratory Charter | S | 6-8 | Single charter + time-box | Product documentation
D-020 | Regression Checklist | M | 10-14 | Full suite maintenance | Test Execution
D-021 | Smoke Test (10 cases) | S | 4-6 | Quick health check | D-024 x10
D-022 | Acceptance Criteria | M | 10-14 | Gherkin features | Requirements
D-023 | Coverage Heatmap | S | 4-6 | HTML dashboard generation | RTM
D-024 | Test Case Template | XS | 2-4 | Standardised format | None
D-025 | Environment Setup | L | 20-24 | K8s + DB + mock services | None
D-026 | Test Data Gen Script | M | 10-14 | Parameterised fixture builder | D-013
D-027 | BDD Feature Suite | L | 16-20 | Cucumber + step definitions | Automation Framework
D-028 | Compliance Audit Log | M | 10-14 | CAA/MAA evidence collection | Test Execution
D-029 | Capacity Plan | S | 6-8 | Resource forecasting | Effort data
D-030 | Go/No-Go Decision Gate | M | 10-14 | Release recommendation | All reports