## Plan
Level Test Plan | L2 | Component
Field | Value
Level ID | L2
Level Name | Component
Focus | Isolated service behaviour with mocks
Techniques | BVA, EP, decision tables, state transition, API contract, pairwise
Test Objects in Scope | Artefact Detector, Coverage Matrix Engine, AI Flag, Clause Library, Evidence Store, Audit Ledger, Classification Boundary
Entry Criteria | Unit tests green; component env ready; mocks configured
Exit Criteria | 90% functional coverage; API contracts verified; component defects triaged
Performance Gates | — (no gate)
Owner Role | Functional Test Engineers
Estimated Effort (hours) | 360
Environment Tier | QA/Test

## Test Objects
Test Object ID | Name | Priority | Notes
TO-001 | Artefact Detector | critical | Coverage matrix seed
TO-002 | Coverage Matrix Engine | critical | p95 <10 min SLA
TO-003 | AI Flag Narrative | high | p95 <30 min SLA
TO-004 | Classification Boundary | critical | Zero cross-tier leakage
TO-005 | Audit Ledger | critical | p95 <500 ms write, RPO zero