## Plan
Level Test Plan | L4 | System
Field | Value
Level ID | L4
Level Name | System
Focus | Full Workbench end-to-end
Techniques | E2E scenarios, load, stress, soak, penetration, WCAG, keystone K1-K8
Test Objects in Scope | All Workbench components
Entry Criteria | Integration complete; system env ready; clause-library revision pinned; test data loaded
Exit Criteria | 100% Noyce SLAs verified; all 17 Gherkin feature files pass; K1-K8 refuse SORA correctly
Performance Gates | Gates 3 Load 8h, 4 Stress 2x, 5 Soak 72h, 8 Twin-sample regression
Owner Role | Functional + perf + security + accessibility engineers
Estimated Effort (hours) | 960
Environment Tier | Perf + System

## Test Objects
Test Object ID | Name | Priority | Notes
TO-001 | Artefact Detector | critical | Coverage matrix seed
TO-002 | Coverage Matrix Engine | critical | p95 <10 min SLA
TO-003 | AI Flag Narrative | high | p95 <30 min SLA
TO-004 | Classification Boundary | critical | Zero cross-tier leakage
TO-005 | Audit Ledger | critical | p95 <500 ms write, RPO zero