## Plan
Level Test Plan | L6 | UAT
Field | Value
Level ID | L6
Level Name | UAT
Focus | Joint CAA/MAA panel runs full approval cycle
Techniques | User-scenario, exploratory, acceptance, panel usability
Test Objects in Scope | Applicant journey + panel journey + post-decision
Entry Criteria | SIT complete; UAT env loaded; twin-sample fixtures; panel briefed
Exit Criteria | Joint panel completes 1 approve + 1 refuse + 1 return; DDH accepts
Performance Gates | Gate 8 (secondary) Twin-sample regression in production-like
Owner Role | Real CAA/MAA inspectors + DDH + RAISO
Estimated Effort (hours) | 120
Environment Tier | UAT

## Test Objects
Test Object ID | Name | Priority | Notes
TO-001 | Artefact Detector | critical | Coverage matrix seed
TO-002 | Coverage Matrix Engine | critical | p95 <10 min SLA
TO-003 | AI Flag Narrative | high | p95 <30 min SLA
TO-004 | Classification Boundary | critical | Zero cross-tier leakage
TO-005 | Audit Ledger | critical | p95 <500 ms write, RPO zero