## Estimation
ID | Deliverable | Optimistic (hrs) | Expected (hrs) | Pessimistic (hrs) | PERT (hrs) | Risk | Phase
T-001 | Test Strategy Document | 4 | 8 | 16 | 8.7 | Low | Design
T-002 | Risk Assessment Matrix | 3 | 6 | 12 | 6.5 | Low | Design
T-003 | RTM (100 clauses) | 8 | 16 | 32 | 17.3 | Medium | Design
T-004 | E2E Chain Test Cases (10) | 10 | 20 | 40 | 21.7 | Medium | Design
T-005 | Integration Test Cases (20) | 15 | 30 | 60 | 32.5 | Medium | Design
T-006 | Decision Tables (3) | 6 | 12 | 24 | 13 | Medium | Design
T-007 | Test Data Packs (6) | 12 | 24 | 48 | 26 | High | Design
T-008 | API Automation (10 endpoints) | 20 | 40 | 80 | 43.3 | High | Execution
T-009 | UI E2E Automation (5 chains) | 16 | 32 | 64 | 34.7 | High | Execution
T-010 | Integration Test Execution (20) | 12 | 24 | 48 | 26 | Medium | Execution
T-011 | Regression Test Suite (50) | 20 | 40 | 80 | 43.3 | High | Execution
T-012 | Performance Load Testing | 16 | 32 | 64 | 34.7 | High | Execution
T-013 | Security Scanning & Red Team | 12 | 24 | 48 | 26 | High | Execution
T-014 | Defect Triage & Reporting | 8 | 16 | 32 | 17.3 | Medium | Reporting
T-015 | Final Test Report | 6 | 12 | 24 | 13 | Low | Reporting
T-016 | Automation Framework Maintenance | 8 | 16 | 32 | 17.3 | Medium | Maintenance
T-017 | CI/CD Integration & DevOps | 12 | 24 | 48 | 26 | High | Automation
T-018 | Keyword-Driven Library Build | 6 | 12 | 24 | 13 | Medium | Automation
T-019 | Data-Driven Test Generator | 8 | 16 | 32 | 17.3 | High | Automation
T-020 | BDD Gherkin Feature File Suite | 10 | 20 | 40 | 21.7 | Medium | Automation
T-021 | Exploratory Testing Charter | 4 | 8 | 16 | 8.7 | Low | Design
T-022 | Accessibility Testing (WCAG 2.1) | 8 | 16 | 32 | 17.3 | Medium | Execution
T-023 | Compliance Audit Trail Verification | 6 | 12 | 24 | 13 | Medium | Execution
T-024 | Production Smoke Test (10 min) | 2 | 4 | 8 | 4.3 | Low | Execution
T-025 | Capacity Planning & Resource Mgmt | 4 | 8 | 16 | 8.7 | Low | Design
TOTAL | 25 deliverables |  |  |  | 511.3