## ARCI
Activity | MAA Lead Inspector | CAA Inspector (AAA) | CAA Innovation Hub | MAA-CTS/QinetiQ | Workbench QA Lead | Workbench Test Manager | Workbench Product Owner | DDH/ODH | RAISO | Range Safety Officer | AAIB Liaison
Strategy approval | A | R | C | I | R | C | C | I | C | I | I
Test scope sign-off | A | R | C | I | R | C | C | I | I | I | I
Risk class assignment | R | A | C | C | C | I | I | C | I | I | I
Test environment provisioning | I | I | I | A | R | C | C | I | I | I | I
Test data prep | I | I | I | A | A | R | C | I | I | I | I
Test execution | I | C | I | C | R | A | I | I | I | I | I
Defect triage | I | A | I | C | R | C | I | I | I | I | I
Exit criteria decision | A | A | R | C | C | C | I | I | C | I | I
Regulatory calibration audit | R | A | A | I | I | C | I | C | C | I | C
Drift monitor review | A | C | I | C | R | C | I | C | I | I | C
Red-team coordination | I | C | C | A | I | R | I | I | C | I | I
Twin-sample regression gate | A | R | C | C | I | I | C | C | I | C | I
Release decision | A | A | R | C | I | I | C | C | I | I | A

## Policies
Policy ID | Title | Description | Applies To | Severity
P1 | Zero Defect Pre-Release | No open critical/major defects in release bundle | All phases | Mandatory
P2 | Keystone Coverage Gate | All 8 keystones must have 90%+ test coverage before exit | Phase 1-2 | Mandatory
P3 | Twin-Sample Regression | Regression pack re-executed on any classifier update | Phase 2-3 | Mandatory
P4 | Regulatory Audit Trail | All test execution evidence stored with audit timestamp | All phases | Mandatory
P5 | Configuration Lock | Test environment config locked 48h before regulatory execution | Phase 2 | Mandatory

## Decision Rights
Decision | Authority | Threshold | Escalation Path
Risk Class Assignment | CAA Inspector + MAA Lead | Unanimous agreement | CAA Head of Innovation Hub
Test Scope Reduction | MAA Lead + CAA AAA | Impact < 5% coverage | Regulatory Steering Committee
Exit Criteria Waiver | MAA Lead + RAISO | Risk mitigation in place | CAA Head of Standards
Schedule Slip | Workbench Product Owner | >2 weeks delay | Programme Sponsor
Environment Rebase | MAA-CTS + QinetiQ | Regression pack re-run required | Workbench QA Lead approval
Defect Severity Override | AAIB Liaison + Workbench QA Lead | Engineering evidence required | CAA Chief Inspector