# MASTER TEST PLAN

CAA/MAA Joint Approval Workbench v1.0

2026-04-23

## Document Control

| Version | v1.0 |
| --- | --- |
| Date | 2026-04-23 |
| Author | Test Manager |
| Status | For Approval |

## Approvals

| Role | Date | Sig |
| --- | --- | --- |
| MAA Lead Inspector | ___/___/___ |  |
| CAA Innovation Hub | ___/___/___ |  |
| Product Owner | ___/___/___ |  |

# Table of Contents

# 1. Project Identification

CAA/MAA Joint Approval Workbench Test Programme | v1.0 | 40 weeks | 19.1 FTE | 4,094 hours

# 2. Scope & Objectives

Ensure regulatory defensibility, operability, safety through risk-based testing (ISO 29119-3, TMap, AMLAS).

# 3. Test Approach

31 techniques across 8 categories: Specification-based, Experience-based, Model-based, Performance & Load, Security, AI/ML, Accessibility, Regression & Release

Twin-sample regression: Scotland PDRA-01 <30 min approval, SORA swarm <30 min refusal

# 4. Schedule & Milestones

Phase 0 (W1-4): Preparation | Phase 1 (W5-12): Intake | Phase 2 (W13-22): Coverage | Phase 2b (W20-26): UI | Phase 2c (W24-32): Classification | Phase 3 (W27-34): Panel | Phase 3b (W33-40): Decision

Key: W2 strategy approved, W4 smoke ready, W8 artefact detector done, W34 twin-sample done, W40 DDH approval

# 5. Resources (19.1 FTE)

Test Manager (1.0), QA Lead (1.2), Functional Engineers (5.4), Perf Engineer (1.8), Security (1.5), Accessibility (1.2), Automation (2.8), Data Engineer (1.2), SME (1.5), Test Analyst (0.5)

# 6. Entry & Exit Criteria

Exit: Twin-sample <30 min both | 69-scenario >95% | K1–K8 conf ≥9 | Cerf PE 1–8 green | WCAG 2.2 AA clean | DAST zero crit/high | Classification zero leakage | DDH approved

# 7. Risk Management

Coverage Matrix complexity | Classified enclave delay | Rare specialist skills

# 8. Deliverables

Test cases (50–100 per phase), functional/security/perf reports, WCAG audit, coverage matrix, regression suite, acceptance checklist

# 9. Change Control

Minor: TM approves | Major: MAA/CAA/PO review | Release-blocking: MAA Lead Inspector

# 10. Approval Sign-Off

| Role | Name | Date | Signature |
| --- | --- | --- | --- |
| MAA Lead Inspector |  | ___/___/___ |  |
| CAA Innovation Hub |  | ___/___/___ |  |
| Product Owner |  | ___/___/___ |  |
| DDH Officer |  | ___/___/___ |  |
| RAISO |  | ___/___/___ |  |