## Quality Risks
Test Object | Type | Probability | Impact | Risk Score | Risk Class | Intensity | Coverage Target %
Artefact Detector Service | Backend Service | High | High | 9 | A | Thorough | 90
PDF Parser Module | Library Integration | High | High | 9 | A | Thorough | 90
Confidence Scorer | Algorithm | Medium | High | 7 | B | Standard | 80
Explainability Engine | Backend Service | Medium | High | 7 | B | Standard | 80
Drift Detection System | Monitoring | Medium | Medium | 6 | B | Standard | 75
Twin-Sample Regression | Test Framework | Low | High | 6 | B | Standard | 75
Document Archive Store | Database | Low | Medium | 4 | C | Light | 60
Red-Team Attack Surface | Security | High | Medium | 8 | A | Thorough | 85
User Enrollment API | REST Service | Medium | Medium | 6 | B | Standard | 70
Performance Load Balancer | Infrastructure | Medium | High | 7 | B | Standard | 80
Authentication/RBAC | Security | Low | High | 6 | B | Standard | 75
Audit Log Completeness | Logging | Low | Medium | 4 | C | Light | 65
Data Immutability Guarantee | Data Governance | Low | High | 6 | B | Standard | 80
Regulatory Compliance Mapping | Process | Low | High | 6 | B | Standard | 70
Accessibility (WCAG AA) | Frontend | Medium | Low | 4 | C | Light | 60
Browser Compatibility | Frontend | Low | Medium | 4 | C | Light | 65
Deployment Rollback Procedure | DevOps | Low | High | 6 | B | Standard | 75
Monitoring Dashboard | Operations | Low | Low | 2 | C | Light | 50
AAIB Feedback Integration | Post-decision | Low | Low | 2 | C | Light | 40
Classifier Model Versioning | MLOps | Low | Medium | 4 | C | Light | 65
Test Data Privacy Compliance | Data Governance | Medium | High | 7 | B | Standard | 80
Regression Pack Maintenance | Test Ops | Medium | Medium | 6 | B | Standard | 70
Requirements Traceability | Quality | Low | Medium | 4 | C | Light | 60
Test Environment Stability | Infrastructure | Medium | Medium | 6 | B | Standard | 75
Change Management Process | Governance | Low | Medium | 4 | C | Light | 60

## Mitigations
Mitigation ID | Risk ID | Category | Action | Owner | Target Date | Status
M1 | TO-001 | Preventive | Requirement review + static code analysis | Design Lead | 2024-10-15 | In Progress
M2 | TO-001 | Detective | Unit + integration testing with 90% coverage | QA Lead | 2024-10-30 | In Progress
M3 | TO-001 | Corrective | Defect review board + root cause analysis | Test Manager | 2024-11-30 | Planned
M4 | TO-002 | Preventive | PDF parser library security audit | Security Officer | 2024-10-20 | In Progress
M5 | TO-002 | Detective | Fuzzing + property-based testing | QA Lead | 2024-11-15 | Planned
M6 | TO-004 | Preventive | Explainability requirements sign-off | RAISO | 2024-10-10 | Complete
M7 | TO-008 | Detective | Red-team simulation + adversarial testing | Security Team | 2024-11-20 | Planned
M8 | TO-009 | Preventive | API specification + contract testing | Arch Lead | 2024-10-25 | In Progress
M9 | TO-010 | Detective | Load testing + capacity planning | Perf Lead | 2024-11-10 | In Progress
M10 | TO-020 | Corrective | Versioning + tag + release process | DevOps Lead | 2024-12-01 | Planned

## Programme Risks
Risk | Category | Probability | Impact | Mitigation | Owner
Testability gaps block design | Schedule | Medium | High | Early architecture review + prototyping | Design Lead
Classified enclave has 90-day lead time | Schedule | High | High | Parallel test environment prep | Infrastructure Lead
AI/classification SMEs rare + expensive | Resource | High | Medium | Upskill team + external consulting | HR Lead
JARUS/AMLAS standards still evolving | Technical | Medium | High | Design flexibility + vendor partnerships | Arch Lead
Regulatory interpretation varies by CAA/MAA | Compliance | Low | High | Steering committee alignment + early audits | Governance Lead

## 5x5 Matrix
| Very Low Impact | Low Impact | Medium Impact | High Impact | Very High Impact
Rare (1) | 1 | 2 | 3 | 4 | 5
Unlikely (2) | 2 | 4 | 6 | 8 | 10
Possible (3) | 3 | 6 | 9 | 12 | 15
Likely (4) | 4 | 8 | 12 | 16 | 20
Almost Certain (5) | 5 | 10 | 15 | 20 | 25