## Dashboard
PROGRAMME METRICS | Value | Target | Status
Total Test Cases | 194 | 200 | On Track
Automated Test Cases | 149 | 150 | On Track
Manual Test Cases | 45 | 50 | On Track
Automation Rate (%) | 77 | 75 | Exceeds
Coverage Adequacy (%) | 62.7 | 60 | Exceeds
Requirements Covered | 18 | 20 | On Track
Keystones Adequate | 6 | 8 | Partial
Quality Gates Passing | 8 | 12 | On Track
Blocking Issues | 5 | 0 | At Risk
RESOURCE METRICS | Value | Budget | Status
Total Programme Budget (£M) | 2.84 | 2.84 | On Budget
Planned Schedule (weeks) | 40 | 40 | On Schedule
Team FTE (actual) | 19.1 | 19.5 | Under
Test Infrastructure Cost (£K) | 420 | 450 | Under
QUALITY METRICS (WEEK 36) | Count | Trend | Status
Test Cases Passed | 165 | ↑ | Good
Test Cases Failed | 18 | → | Monitor
Test Cases Blocked | 8 | ↓ | Improving
Test Cases Skipped | 3 | → | Stable
Defect Density (per KLOC) | 3.2 | ↓ | Improving
Critical Defects Open | 2 | → | Monitor
Major Defects Open | 7 | ↑ | At Risk
Minor Defects Open | 12 | → | Monitor

## Pass Rate Trend
Sprint | Total TCs Run | Passed | Failed | Pass Rate % | Defect Density | Coverage %
S1 | 45 | 42 | 3 | 93.3 | 1.5 | 35
S2 | 52 | 48 | 4 | 92.3 | 1.8 | 40.2
S3 | 58 | 54 | 4 | 93.1 | 1.7 | 44.8
S4 | 65 | 60 | 5 | 92.3 | 2.1 | 50.3
S5 | 72 | 68 | 4 | 94.4 | 1.9 | 55.1
S6 | 78 | 74 | 4 | 94.9 | 1.8 | 59.2
S7 | 85 | 81 | 4 | 95.3 | 1.6 | 62.7
S8 | 92 | 87 | 5 | 94.6 | 2 | 65.1
S9 | 100 | 94 | 6 | 94 | 2.3 | 68
S10 | 108 | 102 | 6 | 94.4 | 2.1 | 70.5
S11 (forecast) | 110 | 105 | 5 | 95.5 | 1.9 | 72

## Defect Trends
Sprint | Open Critical | Open Major | Open Minor | Resolved | Net Change
S1 | 0 | 0 | 0 | 0 | 0
S2 | 0 | 1 | 2 | 0 | 3
S3 | 0 | 2 | 4 | 0 | 2
S4 | 1 | 3 | 6 | 1 | 2
S5 | 1 | 3 | 7 | 2 | -2
S6 | 1 | 2 | 9 | 3 | -1
S7 | 2 | 4 | 10 | 5 | -1
S8 | 2 | 6 | 11 | 4 | 2
S9 | 2 | 7 | 12 | 8 | -1
S10 | 2 | 7 | 12 | 10 | -2
S11 (forecast) | 2 | 5 | 10 | 12 | -4

## Quality Gates Status
Gate | Pass Criteria | Current Status | Evidence | Owner | Target Date
Gate 1: Design Verification | All TCs created + reviewed | PASS | PR #4521 merged | Design Lead | 2024-10-15
Gate 2: Functional Complete | 95% pass rate, all FR tested | PASS | Test report TR-042 | QA Lead | 2024-10-22
Gate 3: Performance Baseline | Response time < 500ms p95 | PASS | Perf report PR-036 | Perf Lead | 2024-10-29
Gate 4: Accuracy Confirmation | >= 60% on Scotland dataset | PASS | Accuracy audit AA-015 | Data Lead | 2024-11-05
Gate 5: Load & Scalability | 1000 req/sec sustained | PASS | Load test LT-028 | Perf Lead | 2024-11-12
Gate 6: Regression Baseline | Pre/post comparison < 2% | PASS | Regression report RR-031 | QA Lead | 2024-11-19
Gate 7: Data Integrity | Hash verification complete | PASS | Data audit DA-044 | Data Lead | 2024-11-26
Gate 8: Security & Compliance | Zero critical vulnerabilities | PENDING | Pen test in progress | Security Lead | 2024-12-03
Gate 9: Red Team Complete | All adversarial vectors tested | PENDING | Red-team exec phase 2 | Security Lead | 2024-12-10
Gate 10: User Acceptance | UAT sign-off from CAA | PENDING | UAT scheduled Dec 15 | Product Owner | 2024-12-15
Gate 11: Deployment Readiness | Rollback procedure verified | PENDING | Deployment plan review | DevOps Lead | 2024-12-20
Gate 12: Release Decision | Steering committee approval | NOT STARTED | Scheduled for Jan 2025 | Sponsor | 2025-01-10

## Burndown template
Day | Ideal | Actual | TCs Remaining | TCs Complete | % Complete
Day 1 (Mon) | 100 | 96 | 100 | 0 | 0
Day 2 (Tue) | 90 | 92 | 92 | 8 | 8
Day 3 (Wed) | 80 | 88 | 86 | 14 | 14
Day 4 (Thu) | 70 | 82 | 76 | 24 | 24
Day 5 (Fri) | 60 | 75 | 68 | 32 | 32
Day 6 (Mon) | 50 | 70 | 60 | 40 | 40
Day 7 (Tue) | 40 | 62 | 50 | 50 | 50
Day 8 (Wed) | 30 | 52 | 38 | 62 | 62
Day 9 (Thu) | 20 | 35 | 20 | 80 | 80
Day 10 (Fri) | 10 | 15 | 8 | 92 | 92