## Strategy
Quality Characteristic | Risk Class | Techniques | Coverage Target % | Entry Criteria | Exit Criteria | Owner | Timeline
Functional Suitability | A | Specification testing, scenario testing | 95 | Requirements approved | All test cases passed | Test Manager | Week 1-5
Performance Efficiency | A | Load testing, throughput analysis | 90 | Baseline established | Performance thresholds met | Perf Lead | Week 6-8
Compatibility | A | Compatibility matrix testing, regression | 85 | Environment ready | All browsers/OS pass | Integration Lead | Week 9-10
Usability | B | User testing, UAT | 70 | Wireframes approved | User acceptance confirmed | UX Lead | Week 11-12
Reliability | A | MTBF testing, error handling | 90 | Test harness ready | Stability metrics met | QA Lead | Week 13-15
Security | A | Penetration testing, vulnerability scan | 95 | Security checklist signed | No critical vulnerabilities | Security Officer | Week 16-18
Maintainability | C | Code review, documentation audit | 60 | Code base complete | Docs reviewed & approved | Tech Lead | Week 19-20
Portability | B | Platform testing, deployment tests | 75 | Deployment scripts ready | Deploys successfully | DevOps Lead | Week 21-22

## QEST
Quality | Prevention | Static Analysis | Dynamic Testing | Correction
Functional Correctness | Requirements review | AST, type checking | Unit + Integration tests | Defect fix + retest
Performance | Capacity planning | Static profiling | Load + stress tests | Optimization + retesting
Security | Threat modeling | SAST, dependency scan | DAST, pen testing | Patch + security audit
Reliability | Fault tree analysis | Complexity metrics | Failure mode injection | Root cause fix
Usability | Design review | UI inspection | User testing sessions | UX refinement
Maintainability | Coding standards | Code duplication check | Manual code review | Refactor + documentation
Compatibility | Platform matrix | Version compatibility | Cross-browser/OS test | Adapter implementation
Portability | Deployment planning | Config validation | Deployment smoke test | Deployment fix

## Intensity
Intensity Level | Risk Class A | Risk Class B | Risk Class C
Thorough | 95% coverage, all techniques, 2+ levels | 80% coverage, primary techniques | 60% coverage, basic smoke test
Standard | 80% coverage, key workflows | 70% coverage, primary paths only | 50% coverage, happy path
Light | 60% coverage, critical only | 50% coverage, critical only | 40% coverage, minimum

## By Phase
Phase | Focus Areas | Test Types | Scope | Owner
Phase 1: Applicant | Functional completeness, performance baseline | Unit, component, system | 80% scope | Applicant + Workbench QA
Phase 2: Regulator | Regulatory compliance, edge cases, security | System, integration, UAT | 100% scope | CAA/MAA + Workbench
Phase 3: Post-decision | Regression, field drift, production monitoring | Smoke, exploratory, production | Critical paths | AAIB + DDH